## Slide 1
CMMS Roles, Responsibilities
& Workflow Standards
Tennant Creek Mine | Gold Processing Plant
TCMG-STD-RACI-001 Rev A
TCMG-STD-RACI-001 | Tennant Creek Mine | Confidential
1 / 10

## Slide 2
Agenda
01
Key CMMS Roles at TCMG
02
RACI Matrix — Who Does What
03
Work Order Lifecycle Flowchart
04
Purchase Request Approval Flow
05
PM Scheduling & Execution Flow
06
Escalation & Exception Handling
07
Role-Based Access Summary
08
Key Contacts & Governance
TCMG-STD-RACI-001 | Tennant Creek Mine | Confidential
2 / 10

## Slide 3
Key CMMS Roles at TCMG
Maintenance Superintendent
Approves WOs, signs off hierarchy changes, owns governance
Maintenance Planner
Creates WOs, plans scope/parts/labour, schedules PMs
Maintenance Supervisor
Assigns crew, approves PRs, ensures field execution quality
Trades (Mech/Elec)
Executes WOs, reports findings, completes PM checklists
Stores Officer
Manages inventory, receives goods, maintains stock codes
Site Administrator
System admin, user permissions, manages CMMS configuration
TCMG-STD-RACI-001 | Tennant Creek Mine | Confidential
3 / 10

## Slide 4
RACI Matrix — Who Does What
Process | Supt | Planner | Supervisor | Trades | Stores | Admin
Raise Work Order | A | R | C | I | - | I
Plan WO (scope/parts) | I | R | C | I | C | -
Schedule WO | A | R | I | I | - | -
Execute WO | I | I | A | R | - | -
Close WO | A | C | R | C | - | -
Raise Purchase Request | A | R | R | I | C | -
Approve PR (value-based) | R | - | A | - | - | I
Create Purchase Order | I | R | - | - | C | -
Receive Goods on Site | - | I | C | I | R | -
Schedule PM | A | R | - | I | - | -
Execute PM Checklist | - | I | A | R | - | -
Manage User Access | A | - | - | - | - | R
Hierarchy / MOC Changes | R | C | I | - | - | A
R = Responsible
A = Accountable
C = Consulted
I = Informed
TCMG-STD-RACI-001 | Tennant Creek Mine | Confidential
4 / 10

## Slide 5
Work Order Lifecycle
Planning
Planner
Planned
Planner
Scheduled
Planner
Active
Trades
On Hold
Supervisor
Completed
Supervisor
Closed
Supt
Can return to Active
Key Rules
100% planning checklist before 'Planned': Asset, Description, Scope, Parts, Labour
Duplicate WO clones record with new number, resets to 'Planning'
'Mark Complete' requires mandatory execution comment and sign-off
Only Superintendent can close a Work Order
'On Hold' requires documented reason; auto-flags after 7 days
TCMG-STD-RACI-001 | Tennant Creek Mine | Confidential
5 / 10

## Slide 6
Purchase Request Approval Flow
Draft PR
Planner/Super
Submitted
Auto-route
Supervisor
Approval
Supervisor
Mgmt
Approval
Supt/SM
Approved
System
PO Created
Planner
Rejected
Returns to Draft with reason
Approval Thresholds
Tier | Value | Approver
Tier 1 | < $5,000 | Maintenance Supervisor
Tier 2 | $5,000 - $25,000 | Maintenance Superintendent
Tier 3 | > $25,000 | Site Manager
TCMG-STD-RACI-001 | Tennant Creek Mine | Confidential
6 / 10

## Slide 7
PM Scheduling & Execution Flow
PM Template
Defined
Planner
Linked to
Asset
Planner
Frequency
Set
Planner
Auto-Generate
WO
System
Assign to
Crew
Supervisor
Execute
Checklist
Trades
Record
Findings
Trades
Close &
Sign-off
Supervisor
PM Governance
All PMs linked to an asset via PM-Asset Staging table before go-live
PM frequency: Daily, Weekly, Monthly, Quarterly, 6-Monthly, Annual, Shutdown-only
Overdue PMs auto-flag and escalate to Superintendent after 48 hours
PM compliance target: 90% minimum monthly completion rate
TCMG-STD-RACI-001 | Tennant Creek Mine | Confidential
7 / 10

## Slide 8
Escalation & Exception Handling
Scenario | Action | Escalation To | Timeframe
WO On Hold > 7 days | Auto-flag in system | Superintendent | Immediate
PM Overdue > 48 hrs | Escalation notification | Superintendent | 24 hrs to resolve
PR Rejected twice | Review meeting triggered | Superintendent + SM | Within 48 hrs
Goods not received by ETA | Supplier follow-up | Stores + Planner | Day after ETA
Emergency breakdown WO | Skip planning phase | Supervisor direct | Immediate
Hierarchy change request | MOC process triggered | Superintendent | Formal review
All escalations are logged in the audit trail for governance compliance.
TCMG-STD-RACI-001 | Tennant Creek Mine | Confidential
8 / 10

## Slide 9
Role-Based Access Summary
Module | Superintendent | Planner | Supervisor | Trades | Stores | Admin
Work Orders | Full | Full | Full | Execute only | - | Full
Purchase Requests | Approve | Create/Edit | Create/Approve | View | View | Full
PO Tracker | View | Full | View | View | Full | Full
PM Templates | Approve | Full | View | View | - | Full
Asset Hierarchy | Approve MOC | Edit | View | View | - | Full
Stores/Inventory | View | View | View | - | Full | Full
User Management | - | - | - | - | - | Full
Reporting | Full | Full | View | View | View | Full
Full = Create/Edit/Delete/Approve View = Read-only - = No access
TCMG-STD-RACI-001 | Tennant Creek Mine | Confidential
9 / 10

## Slide 10
Governance & Key Contacts
This document is the single source of truth for CMMS roles and responsibilities
All changes require formal Management of Change (MOC) approval
Annual review required — Next review: March 2027
All CMMS actions logged via audit trail for compliance
Practice mode available for training — no production data affected
Document Owner
Maintenance Superintendent
System Admin
Site Administrator
Planning Lead
Maintenance Planner
TCMG-STD-RACI-001 | Rev A | Tennant Creek Mine
TCMG-STD-RACI-001 | Tennant Creek Mine | Confidential
10 / 10